## Slide 1: Whole Family Wellbeing 2023-24
Programme Proposals

## Slide 2: Current Progress
£32m to CSPPs.
Evaluation - Initial findings report
3 collaborative partnerships started
Learning into Action Network
Element 3
Governance

## Slide 3: Emerging challenges
Recruitment and resource: Bureaucracy and availability slowing implementation
Budget: Clarity around WFWF recurring budgets; uncertainty around wider core budgets; alignment and reporting across funding
Support, challenge and accountability: How to support CSPPs which are at earlier developmental stage; comms and engagement; understanding progress
Cross-agency approach: Third sector engagement in planning and delivery; connections with child poverty activity
Evaluation: Proportionality and supporting learning and delivery

## Slide 4: Priorities for 2023-24
Maintaining current activity
Initiating new activity to address emerging learning
Addressing emerging issues through design of activity

## Slide 5: Proposed programme approach
E1 – Enabling local WFS activity across all CSPPs
E2 – National activity to support local whole system change:
  3 collaborative partnerships, Learning into Action network, self assessment toolkit, evaluation and research, commissioning and procurement project
  Being considered: Cross-portfolio prevention activity; Third sector development; data and evidence; targeted local action
  E3 – Cross portfolio policy led activity to support development of holistic family support services

## Slide 6: Questions
What are the emerging challenges to implementation?
What should our priorities be to support ongoing implementation of whole system change for holistic family support?
What are the practical connections with Promise implementation that we should build in to these proposals?