The Promise Highlight Report March 2022

Achievements to date

- Well established Local Oversight Board

- Promise Operational Group meets 6 weekly

- Agreed governance framework locally for the Promise work

- Increased the number of Children and Young People involved in Strategic and Operational Groups and supported them to take part

- Agreed and progressing two workstreams (1)Communications and Language and (2)Alternative Care with young people co-chairing both working groups

- We have implemented our communication, participation and engagement plans

- Implementation of our ‘Keeping Sisters and Brothers Together’ policy

- We have identified local priorities and objectives

- We have undertaken a Discovery Mapping exercise

- Champions Board members and care experienced young people involved in decision making and co-design of the language used in the care system

- We have one ‘Promise Design Champion’

Promise and Team Updates

- Merchandise identified and branding agreed, ordered and delivered

- Promise Partnership ‘Brothers and Sisters funding’ applied for successfully. This will cover two, two-year posts: one Learning and Development and the other Family support

- Staff Briefings continue to be published

- Involving young people in live interviews

- Half day Development Day carried out looking at priorities – one further day planned

- Contact made with locality social workers about children and young people looked after at home

- Delivering awareness and training sessions including the connected leadership conference. (Now over 70 presentations delivered)

- Engagement with third parties

- Promise Design School Support to rebrand and attended catch ups

- Attendance at Corporate Parenting Steering Group agreed for two young people.

- Assisting SCRA to advertise young people being involved in panel meetings

- Champions Board commenting on Housing ‘Customer Connections’ draft policy

- Promise ‘Champions’ Sharepoint site set up

- Advertising shortly for a Care Experienced Participation assistant

- Hoping to get a Care Experienced Modern Apprentice on board

- Advertising shortly for sessional workers

Next Steps

- Further targeted presentations for Stage 2 services

- Discovery Mapping

- Increasing staffing of the team to take forward the Promise work

- More engagement events planned, including the Promise Convention (rescheduled from 14 February 2022)

- Initiate the 2 working groups through the PrOG

- Develop training and schedule for young people being involved in interviews

- Looking at starting a care experienced youth group and researching into having participation assistants

- Planning to have a promise design champion. Identified young people who would be interested.

- Gain access to ‘Looked After Young People at Home’ through schools

- Create two Youth Forums for care Experienced Young People

- Promise Conference for September

- Easter event planned

- Summer programme being planned

- Corporate Parenting Plan and Annual report to be completed

Challenges

- Cancelled Promise Conference and Family Christmas lunch for vulnerable families

Corporate Parenting Team

March 2022