The Promise Highlight Report March 2022

Achievements to date

- Well established Local Oversight Board

- Promise Operational Group meets 6 weekly

- Agreed governance framework locally for the Promise work

- Increased the number of Children and Young People involved in Strategic and Operational Groups and supported them to take part

- Agreed and progressing two workstreams (1)Communications and Language and (2)Alternative Care with young people co-chairing both working groups, another two being created: Mapping and Trauma informed groups to be established

- We have started to implement our communication, participation and engagement plans

- Implementation and embedding of our ‘Keeping Sisters and Brothers Together’ policy

- We have identified local priorities and objectives

- We have undertaken a Discovery Mapping exercise with partners

- Champions Board members and care experienced young people involved in decision making and co-design of the language used in the care system

- We have one ‘Promise Design Champion’

Promise Team Update

- Merchandise identified and branding agreed, ordered and delivered

- Promise Partnership ‘Brothers and Sisters funding’ applied for successfully. This will cover two, two-year posts

- Staff Briefings continue to be published

- Involving young people in live interviews

- Half day Development Day carried out looking at priorities – one further day planned

- Delivering awareness and training sessions including the connected leadership conference. (Now over 70 presentations delivered)

- Engagement with third parties

- Promise Design School Support to rebrand and attended catch ups

- Assisting SCRA to get more young people being involved in panel meetings

- Champions Board commenting on Housing draft policy

- Promise ‘Champions’ Sharepoint site set up & working on website

- Advertising shortly for a Care Experienced Participation Assistant

- Hoping to get a Care Experienced Modern Apprentice on board

- Advertising shortly for sessional workers

Next Steps

- Further targeted presentations for Stage 2 services

- Further discovery mapping

- Draft Anti-Stigma and Language policy – out for comment then finalise

- Creation of a local ‘Promise Two Years On’ report - collating evidence and benchmarking against national 2021-2024 plan

- Increasing staffing of the team to take forward the Promise work

- More engagement events planned, including the Promise Conference (rescheduled from 14 February 2022)

- Initiate a further 2 working groups through the PrOG

- Develop further training and schedule for young people being involved in interviews

- Looking at starting a care experienced youth group and research ongoing into having Participation Assistants

- Planning to have a young person’s Promise Design Champion. Identified young people who would be interested.

- Further support for ‘Looked After Young People at Home’

- Create two Youth Forums for Care Experienced Young People

- Easter event planned

- Summer programme being planned

- Corporate Parenting Plan and Annual report to be completed

Challenges

- Cancelled Promise Conference and Family Christmas lunch for families due to Covid restrictions - both rescheduled and plans well underway to hold on new dates